| Production schedule: Dates and Deadlines |
| --- |
| Title: | Cadbury’s Flashmob |
| Client: | Cadbury’s |
| Producer: | No Face Films |
| Director: | Raihan Muhammad |
| Date: | 24.02.11 |

| Programme start: |  | Programme completed: |  |
| --- | --- | --- | --- |
| Stixy | 02.01.11 | Completed: | 05.01.11 |
| Proposal start | 24.12.10 | Completed: | 07.01.11 |
| Agreement from client |  |  |  |
| Storyboard start | 03.02.11 | Completed: | 08.02.11 |
| Location recce | 18.02.11 | Completed: | 18.02.11 |
| Production start: FILMING | 05.04.11 | Completed: | 05.04.11 |
| Post Production start: EDITING | 06.04.11 | Completed: | 06.04.11 |
| 1st Draft to client | 08.04.11 | Completed: | 08.04.11 |
| START FILMING |  | Completed: |  |